## README
DatIQ Feature & Release Tracker
v1.0 · August 2026 · Companion to Files 01–12 (Model Council deliverables & implementation prompts)
Sheet | Purpose
Feature Master | One row per roadmap feature (Files 02, 08–12). Traceability: Feature -> Prompt -> Release -> Source report. Update the yellow status columns as work progresses.
Prompt Runbook | Ordered execution list of implementation prompts. Run top to bottom; respect Run-After column.
Release Milestones | Release/version windows, themes, exit criteria. Feature counts and effort auto-roll up from Feature Master via formulas.
Docs & Content | Per-prompt documentation contract checklist (feature doc, help, use case, changelog, blog, runbook).
RAID Log | Risks, Assumptions, Issues, Dependencies — seeded from council analysis; maintain continuously.
Legend | Yellow-filled cells are the ones you edit (statuses, dates, owners, notes). All other cells are reference data or formulas.
Status values | Planned / In Progress / Built / Testing / Deployed-Canary / GA / Deferred / Skipped(trigger)
Source key | MM=MiniMax analysis · CL=Claude blueprint · DS=DeepSeek/ZAi blueprints · GM=Gemini platform paper · LS=Live-site review · CO=Council addition

## Feature Master
Feature ID | Feature Name | Pillar | Release | Version | Milestone Window | Prompt ID | Flag | Source Reports | Composite Score | Primary Persona(s) | Tier Gate | Est PD | Dependencies | Success Metric | Status | Build | Test | Docs | Deploy | Owner | Target Date | Notes
F-000 | Platform bootstrap (flags, docs pipeline, CI gates, golden datasets, telemetry taxonomy) | Platform | R0 | v1.1 | Wk 1-4 | DP-R0-00 | n/a | CO |  | Engineering | n/a | 3 | — | CI green; changelog assembler works | Planned
F-0.1 | SSR + deep-linkable result permalinks | Growth | R0 | v1.1 | Wk 1-4 | DP-R0-01 | permalinks | MM | 4.55 | All | Free+ | 5 | F-000 | >50 indexed pages; share events | Planned
F-0.2 | One-click JSON/CSV/Markdown export | Extract | R0 | v1.1 | Wk 1-4 | DP-R0-02 | export | MM, DS | 4.5 | Analyst, Developer | Free+ | 2 | F-000 | Export usage; conversion assist | Planned
F-0.3 | REST API v1 + keys + OpenAPI docs | Platform | R0 | v1.1 | Wk 1-4 | DP-R0-03 | public_api | CL, DS | 4.4 | Developer | Starter+ | 7 | F-0.2 | Keys created; API req volume | Planned
F-0.4 | Persona landing routes (5 incl. /ai-visibility) | Growth | R0 | v1.1 | Wk 1-4 | DP-R0-04 | persona_routes | MM, GM | 4.3 | All | n/a | 3 | F-0.1 | Per-route signup conversion | Planned
F-0.5 | Programmatic SEO engine | Growth | R0 | v1.1 | Wk 1-4 | DP-R0-05 | pseo | MM | 4.2 | All | n/a | 3 | F-0.1,F-0.4 | Indexed count; organic clicks | Planned
F-0.6 | Accounts + saved history + collections | App Shell | R0 | v1.1 | Wk 1-4 | DP-R0-06 | collections | MM, GM | 4.15 | All | Free+ | 4 | F-000 | Return-visit rate; items saved | Planned
F-0.7 | Public changelog + docs hub + PH/social launch | Growth | R0 | v1.1 | Wk 1-4 | DP-R0-07 | docs_hub | MM | 4.1 | All | n/a | 5 | F-000 | Docs views; PH launch executed | Planned
F-0.8 | Rebrand rollout (identity, homepage, pricing page) | Brand | R0 | v1.1 | Wk 1-4 | DP-R0-09 | rebrand_2026 | All | 4.1 | All | n/a | 7 | F-0.4 | Hero A/B conversion | Planned
F-0.9 | Modular routing shell + feature flags | Platform | R0 | v1.1 | Wk 1-4 | DP-R0-00 | n/a | CL | 4 | Engineering | n/a | 3 | F-000 | Routes live behind flags | Planned
F-0.10 | Webhooks v1 (extraction/batch/schedule events) | Platform | R0 | v1.1 | Wk 1-4 | DP-R0-08 | webhooks | CL, DS | 3.95 | Developer | Starter+ | 3 | F-0.3 | Deliveries; recipes created | Planned
F-0.11 | Analytics foundation + activation instrumentation | Platform | R0 | v1.1 | Wk 1-4 | DP-R0-10 | n/a | CL, CO |  | Founder/PM | n/a | 2 | F-000 | Weekly digest received | Planned
F-1.1a | Social ingestion pipeline (X, Reddit, RSS) | Social | R1 | v2.0 | Wk 5-12 | DP-R1-01 | social_pipeline | CL, DS | 4.45 | CMO, Founder | Starter+ | 6 | F-000 | Ingest SLAs met 72h | Planned
F-1.1b | Sentiment + intent classification + NER + reach | Social | R1 | v2.0 | Wk 5-12 | DP-R1-02 | social_pipeline | DS, CL | 4.45 | CMO, RevOps | Starter+ | 5 | F-1.1a | Golden gate: 80%/70% agreement | Planned
F-1.1c | Social dashboard + mention feed + detail | Social | R1 | v2.0 | Wk 5-12 | DP-R1-03 | social_mvp | CL | 4.45 | CMO, Founder | Starter+ | 7 | F-1.1b | Feed DAU; p95 <800ms | Planned
F-1.1d | Keyword tracking + onboarding wizard | Social | R1 | v2.0 | Wk 5-12 | DP-R1-04 | social_mvp | CL | 4.45 | All | Starter+ | 4 | F-1.1c | Wizard completion >=70% | Planned
F-1.1e | Alert engine (spike/negative/influence/co-mention) | Social | R1 | v2.0 | Wk 5-12 | DP-R1-05 | social_alerts | DS, CL | 4.45 | CMO, Founder | Starter+ | 5 | F-1.1b | Alert open rate >=40% | Planned
F-1.2 | Stripe billing + 4 tiers + gates + metering | Monetization | R1 | v2.0 | Wk 5-12 | DP-R1-06 | billing | CL, DS, GM | 4.4 | All | n/a | 8 | F-000 | First live transactions; gate matrix green | Planned
F-1.3 | HubSpot connector (bi-directional) | Connect | R1 | v2.0 | Wk 5-12 | DP-R1-07 | connectors | All | 4.35 | RevOps | Starter+ | 6 | F-1.2 | Syncs completed; zero unresolved errors | Planned
F-1.4 | Apollo connector (enrichment + verification) | Connect | R1 | v2.0 | Wk 5-12 | DP-R1-07 | connectors | All | 4.25 | RevOps | Starter+ | 4 | F-1.2 | Enrichments applied | Planned
F-1.5 | Change-detection alerts on schedules | Compete | R1 | v2.0 | Wk 5-12 | DP-R1-09 | change_alerts | MM, LS | 4.2 | CI/Marketing | Starter+ | 5 | F-0.10,F-1.1e | Changes detected; diff views | Planned
F-1.6 | Connector framework + mapping engine + mgmt UI | Connect | R1 | v2.0 | Wk 5-12 | DP-R1-07 | connectors | CL | 4.05 | RevOps | Starter+ | 6 | F-1.2 | Dry-run adoption; framework reuse | Planned
F-1.7 | Usage dashboard | Monetization | R1 | v2.0 | Wk 5-12 | DP-R1-10 | usage_digests | CL | 4 | All paid | Starter+ | 3 | F-1.2 | Usage views; upgrade CTA clicks | Planned
F-1.8 | Competitive keyword tracking + trend comparison | Compete | R1 | v2.0 | Wk 5-12 | DP-R1-08 | social_compete | CL | 3.95 | CI, CMO | Pro+ | 4 | F-1.1e | Compare views | Planned
F-1.9 | Email digests (daily/weekly) | Engagement | R1 | v2.0 | Wk 5-12 | DP-R1-10 | usage_digests | CL, GM | 3.9 | All | Starter+ | 3 | F-1.1e,F-1.5 | Digest open rate | Planned
F-1.10 | 30-day historical backfill | Social | R1 | v2.0 | Wk 5-12 | DP-R1-08 | social_compete | CL | 3.75 | All | Starter+ | 3 | F-1.1a | Time-to-first-mention <10min | Planned
F-1.11 | LLM semantic-fallback parsing | Extract | R1 | v2.0 | Wk 5-12 | DP-R1-11 | semantic_fallback | DS | 3.75 | All | Free+ | 4 | F-000 | Failure-recovery rate; golden parity | Planned
F-1.12 | Product analytics deep-dive + admin console v1 | Platform | R1 | v2.0 | Wk 5-12 | DP-R1-12 | admin_v1 | CL | 3.7 | Internal | n/a | 5 | F-1.2 | Cohort report generated | Planned
F-1.13 | Onboarding + polish (perf, a11y, mobile) | Quality | R1 | v2.0 | Wk 5-12 | DP-R1-13 | (various) | CL | 3.7 | All | n/a | 9 | All R1 | Lighthouse budgets green | Planned
F-2.1 | Company Intelligence workspace | Company | R2 | v2.5 | M4-6 | DP-R2-01 | company_intel | GM | 4.2 | RevOps, Founder | Starter+ | 12 | R1-RC | Profiles created; accuracy rubric | Planned
F-2.2 | MCP server + agent-ready API | Platform | R2 | v2.5 | M4-6 | DP-R2-02 | mcp_server | MM, DS | 4.15 | Developer | Pro+ | 6 | F-0.3 | 10 external integrations | Planned
F-2.3 | Calendly connector: pre-meeting briefings | Connect | R2 | v2.5 | M4-6 | DP-R2-03 | calendly_briefs | CL | 4.1 | RevOps | Pro+ | 6 | F-2.1,F-1.6 | Briefs generated/opened | Planned
F-2.4 | Competitive Intelligence module + battlecards | Compete | R2 | v2.5 | M4-6 | DP-R2-04 | compete_module | GM, MM | 4.05 | CI, Sales | Pro+ | 10 | F-1.5,F-2.1 | Battlecards created/shared | Planned
F-2.5 | Prebuilt extraction templates (25) | Extract | R2 | v2.5 | M4-6 | DP-R2-05 | templates | MM | 3.85 | All | Free+ | 5 | R1-RC | Templates applied; gallery conversion | Planned
F-2.6 | Zapier + Make + Sheets + Airtable | Connect | R2 | v2.5 | M4-6 | DP-R2-06 | automation_integrations | MM | 3.85 | All | Starter+ | 7 | F-0.10,F-1.6 | Destination syncs; Zapier listing | Planned
F-2.7 | Slack + Teams alert channels | Engagement | R2 | v2.5 | M4-6 | DP-R2-07 | team_surfaces | DS, GM | 3.8 | Teams | Starter+ | 4 | F-1.1e | Deliveries by channel | Planned
F-2.8 | Research Workspace (projects, pins, saved searches) | App Shell | R2 | v2.5 | M4-6 | DP-R2-07 | team_surfaces | GM | 3.75 | Analyst | Starter+ | 5 | F-0.6 | Projects created | Planned
F-2.9 | YouTube + news sources | Social | R2 | v2.5 | M4-6 | DP-R2-08 | sources_v2 | GM, DS | 3.7 | CMO | Pro+ | 4 | F-1.1a | Mentions by new source | Planned
F-2.10 | SOC 2 evidence collection start | Trust | R2 | v2.5 | M4-6 | DP-R2-08 | n/a | CO | 3.6 | Enterprise | n/a | 3 | — | Evidence tracker initialized | Planned
F-2.11 | Mobile + WCAG AA pass (R2 surfaces) | Quality | R2 | v2.5 | M4-6 | DP-R2-08 | n/a | CL | 3.55 | All | n/a | 4 | R2 features | Axe/Lighthouse budgets | Planned
F-3.1 | AI Visibility / AEO monitoring (add-on $99) | Brand/AEO | R3 | v3.0 | M7-9 | DP-R3-01 | ai_visibility | GM, DS | 4.3 | CMO | Add-on | 14 | R2-RC | Attach rate; runs completed | Planned
F-3.2 | Brand Intelligence / Share-of-Voice engine | Brand | R3 | v3.0 | M7-9 | DP-R3-02 | brand_intel | DS, GM | 4.05 | CMO | Business+ | 10 | F-1.8 | Dashboard DAU; incidents opened | Planned
F-3.3 | Verified contact enrichment (trigger-gated) | Extract | R3 | v3.0 | M7-9 | DP-R3-03 | verified_enrichment | MM | 3.9 | RevOps | Pro+ | 6 | F-1.4; GTM trigger | Verified rate; bounce feedback | Planned
F-3.4 | Social Posts Writer & thread generator | Content | R3 | v3.0 | M7-9 | DP-R3-04 | content_writer | DS | 3.8 | CMO, Founder | Pro+ | 7 | R2-RC | Drafts created/exported | Planned
F-3.5 | Community Moderator ($29/seat) | Content | R3 | v3.0 | M7-9 | DP-R3-05 | moderator | DS | 3.65 | Support/CM | Add-on | 6 | F-3.4 | Flags; approved replies | Planned
F-3.6 | LinkedIn/IG/FB public sources (spike-gated) | Social | R3 | v3.0 | M7-9 | DP-R3-06 | sources_v3 | GM, DS | 3.6 | CMO | Pro+ | 8 | F-2.9; spike ADR | Cleared sources live | Planned
F-3.7 | Influencer discovery & reach mapping | Social | R3 | v3.0 | M7-9 | DP-R3-06 | sources_v3 | GM, DS | 3.55 | CMO | Business+ | 3 | F-3.6 | Influencer views | Planned
F-3.8 | Campaign performance tracking | Brand | R3 | v3.0 | M7-9 | DP-R3-07 | campaigns_gallery | GM | 3.5 | CMO | Pro+ | 4 | F-3.2 | Campaigns created | Planned
F-3.9 | Community template gallery + submissions | Growth | R3 | v3.0 | M7-9 | DP-R3-07 | campaigns_gallery | CO | 3.45 | All | Free+ | 4 | F-2.5 | Submissions approved; SEO pages | Planned
F-4.1 | Team workspaces + RBAC + audit logs | Trust | R4 | v3.5 | M10-12 | DP-R4-01 | teams_rbac | CL, DS | 4 | Teams, Agencies | Business+ | 10 | R3-RC | Policy matrix green; audit coverage >=95% | Planned
F-4.2 | SSO/SAML + SOC 2 Type II + privacy posture | Trust | R4 | v3.5 | M10-12 | DP-R4-02 | enterprise_auth | DS, MM | 3.95 | Enterprise | Enterprise | 10 | F-4.1,F-2.10 | SOC 2 issued; first enforced-SSO ws | Planned
F-4.3 | Self-healing extraction + validation layer | Extract | R4 | v3.5 | M10-12 | DP-R4-03 | self_healing | MM, DS | 3.85 | All | Pro+ | 9 | F-1.11 | Auto-repair rate >=85% on fixtures | Planned
F-4.4 | Salesforce + Pipedrive connectors | Connect | R4 | v3.5 | M10-12 | DP-R4-04 | crm_wave2 | CL, GM | 3.8 | Enterprise, EMEA | Business+ | 9 | F-1.6 | Syncs; AppExchange status | Planned
F-4.5 | Executive Intelligence module ($199 add-on) | Executive | R4 | v3.5 | M10-12 | DP-R4-05 | exec_intel | GM | 3.8 | Founder, C-suite | Add-on | 8 | F-2.1,F-2.4,F-3.2 | Briefs generated; founder weekly use | Planned
F-4.6 | Anomaly hardening + PagerDuty + SLOs | Ops | R4 | v3.5 | M10-12 | DP-R4-06 | ops_enterprise | DS | 3.65 | Enterprise | Enterprise | 5 | R3-RC | SLO dashboard live | Planned
F-4.7 | Dedicated proxy pools + data residency (EU/India) | Ops | R4 | v3.5 | M10-12 | DP-R4-06 | ops_enterprise | DS, CO | 3.6 | Enterprise | Add-on | 5 | F-4.6 | Residency-pinned workspace verified | Planned
F-4.8 | Admin console v2 (flag targeting, impersonation) | Platform | R4 | v3.5 | M10-12 | DP-R4-07 | customer_intel | CL | 3.55 | Internal | n/a | 4 | F-1.12 | Support resolution time down | Planned
F-4.9 | Customer Intelligence v1 (reviews/tickets/NPS) | Customer | R4 | v3.5 | M10-12 | DP-R4-07 | customer_intel | GM | 3.45 | Product, CS | Business+ | 7 | F-3.2 | Sources ingested; risks flagged | Planned
F-5.2 | Knowledge Graph foundation (built first) | Graph | R5 | v4.0 | Year 2 | DP-R5-01 | knowledge_graph | GM | 3.95 | All | Business+ | 20 | R4-RC gate | Resolution precision; entity pages | Planned
F-5.1 | Autonomous AI Agents (approval-gated) | Agents | R5 | v4.0 | Year 2 | DP-R5-02 | agents | GM | 4.1 | All | Business+ | 25 | F-5.2,F-2.2 | Agent runs; approval rate | Planned
F-5.4 | Multi-modal ingestion (PDF/DOCX/CSV/AV/email) | Ingest | R5 | v4.0 | Year 2 | DP-R5-03 | multimodal | GM | 3.5 | Analyst | Pro+ | 12 | F-5.2 | Files processed by format | Planned
F-5.5 | Market Intelligence module (TAM/SAM/SOM, maps) | Market | R5 | v4.0 | Year 2 | DP-R5-04 | market_intel | GM | 3.45 | Strategy | Business+ | 10 | F-5.2 | Maps generated | Planned
F-5.6 | Risk Intelligence (vendor/cyber/compliance/ESG) | Risk | R5 | v4.0 | Year 2 | DP-R5-05 | risk_intel | GM | 3.4 | BFSI, Enterprise | Enterprise | 10 | F-5.2 | Pilot partners live | Planned
F-5.3 | Virality prediction & trend forecasting | Social | R5 | v4.0 | Year 2 | DP-R5-06 | platform_economy | GM | 3.5 | CMO | Add-on | 6 | F-1.1e | Forecast accuracy tracked | Planned
F-5.7 | Sub-product packaging (standalone SKUs) | Monetization | R5 | v4.0 | Year 2 | DP-R5-06 | platform_economy | GM | 3.4 | All | n/a | 8 | Council review | SKU checkout E2E | Planned
F-5.8 | Marketplace & partner ecosystem | Platform | R5 | v4.0 | Year 2 | DP-R5-06 | platform_economy | CO | 3.35 | Partners | n/a | 10 | F-5.7 | First partner listing | Planned

## Prompt Runbook
Order | Prompt ID | Title | Release | Version | Run After | Features Covered | Status | Run Date | Agent/Runner | Result Notes
1 | DP-R0-00 | Platform bootstrap | R0 | v1.1 | — | F-000, F-0.9 | Planned
2 | DP-R0-01 | SSR result permalinks | R0 | v1.1 | DP-R0-00 | F-0.1 | Planned
3 | DP-R0-02 | Export JSON/CSV/MD | R0 | v1.1 | DP-R0-00 | F-0.2 | Planned
4 | DP-R0-03 | REST API v1 + keys + docs | R0 | v1.1 | DP-R0-02 | F-0.3 | Planned
5 | DP-R0-04 | Persona landing routes | R0 | v1.1 | DP-R0-01 | F-0.4 | Planned
6 | DP-R0-05 | Programmatic SEO engine | R0 | v1.1 | DP-R0-01,04 | F-0.5 | Planned
7 | DP-R0-06 | History & collections | R0 | v1.1 | DP-R0-00 | F-0.6 | Planned
8 | DP-R0-07 | Changelog + docs hub + launch ops | R0 | v1.1 | DP-R0-00 | F-0.7 | Planned
9 | DP-R0-08 | Webhooks v1 | R0 | v1.1 | DP-R0-03 | F-0.10 | Planned
10 | DP-R0-09 | Rebrand rollout | R0 | v1.1 | DP-R0-04 | F-0.8 | Planned
11 | DP-R0-10 | Analytics foundation | R0 | v1.1 | DP-R0-00 | F-0.11 | Planned
12 | DP-R0-RC | Release cut v1.1 | R0 | v1.1.2 | All R0 | — | Planned
13 | DP-R1-01 | Social ingestion pipeline | R1 | v2.0 | DP-R0-RC | F-1.1a | Planned
14 | DP-R1-02 | Sentiment + intent classification | R1 | v2.0 | DP-R1-01 | F-1.1b | Planned
15 | DP-R1-03 | Social dashboard & feed | R1 | v2.0 | DP-R1-02 | F-1.1c | Planned
16 | DP-R1-04 | Keywords + onboarding wizard | R1 | v2.0 | DP-R1-03 | F-1.1d | Planned
17 | DP-R1-05 | Alert engine & notifications | R1 | v2.0 | DP-R1-02 | F-1.1e | Planned
18 | DP-R1-06 | Stripe billing + tiers + gates | R1 | v2.0 | DP-R0-RC | F-1.2 | Planned
19 | DP-R1-07 | Connector framework + HubSpot + Apollo | R1 | v2.0.1 | DP-R1-06,02 | F-1.3, F-1.4, F-1.6 | Planned
20 | DP-R1-08 | Backfill + competitive tracking + charts | R1 | v2.0.1 | DP-R1-05 | F-1.8, F-1.10 | Planned
21 | DP-R1-09 | Change-detection alerts | R1 | v2.0.1 | DP-R0-08, DP-R1-05 | F-1.5 | Planned
22 | DP-R1-10 | Usage dashboard + digests | R1 | v2.0.2 | DP-R1-06,09 | F-1.7, F-1.9 | Planned
23 | DP-R1-11 | Semantic-fallback parsing | R1 | v2.0.2 | DP-R0-RC | F-1.11 | Planned
24 | DP-R1-12 | Analytics deep-dive + admin v1 | R1 | v2.0.2 | DP-R1-06 | F-1.12 | Planned
25 | DP-R1-13 | Polish: perf, a11y, mobile | R1 | v2.0.3 | All R1 | F-1.13 | Planned
26 | DP-R1-RC | Release cut v2.0 | R1 | v2.0.3 | All R1 | — | Planned
27 | DP-R2-01 | Company Intelligence workspace | R2 | v2.5 | DP-R1-RC | F-2.1 | Planned
28 | DP-R2-02 | MCP server | R2 | v2.5 | DP-R1-RC | F-2.2 | Planned
29 | DP-R2-03 | Calendly pre-meeting briefs | R2 | v2.5.1 | DP-R2-01, DP-R1-07 | F-2.3 | Planned
30 | DP-R2-04 | Competitive Intelligence + battlecards | R2 | v2.5.1 | DP-R1-09, DP-R2-01 | F-2.4 | Planned
31 | DP-R2-05 | Extraction templates | R2 | v2.5.2 | DP-R1-RC | F-2.5 | Planned
32 | DP-R2-06 | Zapier/Make/Sheets/Airtable | R2 | v2.5.2 | DP-R0-08, DP-R1-07 | F-2.6 | Planned
33 | DP-R2-07 | Slack/Teams + Research Workspace | R2 | v2.5.3 | DP-R1-05 | F-2.7, F-2.8 | Planned
34 | DP-R2-08 | Sources v2 + compliance + quality | R2 | v2.5.3 | DP-R1-01 | F-2.9, F-2.10, F-2.11 | Planned
35 | DP-R2-RC | Release cut v2.5 | R2 | v2.5.3 | All R2 | — | Planned
36 | DP-R3-01 | AI Visibility / AEO monitoring | R3 | v3.0 | DP-R2-RC | F-3.1 | Planned
37 | DP-R3-02 | Brand Intelligence / SoV | R3 | v3.0 | DP-R2-RC | F-3.2 | Planned
38 | DP-R3-03 | Verified enrichment (trigger-gated) | R3 | v3.0.1 | DP-R1-07 + trigger | F-3.3 | Planned
39 | DP-R3-04 | Social Posts Writer | R3 | v3.0.1 | DP-R2-RC | F-3.4 | Planned
40 | DP-R3-05 | Community Moderator | R3 | v3.0.2 | DP-R3-04 | F-3.5 | Planned
41 | DP-R3-06 | Sources v3 (spike-gated) + influencers | R3 | v3.0.2 | DP-R2-08 | F-3.6, F-3.7 | Planned
42 | DP-R3-07 | Campaigns + community gallery | R3 | v3.0.3 | DP-R3-02, DP-R2-05 | F-3.8, F-3.9 | Planned
43 | DP-R3-RC | Release cut v3.0 | R3 | v3.0.3 | All R3 | — | Planned
44 | DP-R4-01 | Teams + RBAC + audit | R4 | v3.5 | DP-R3-RC | F-4.1 | Planned
45 | DP-R4-02 | SSO + SOC 2 + privacy | R4 | v3.5 | DP-R4-01 | F-4.2 | Planned
46 | DP-R4-03 | Self-healing extraction | R4 | v3.5.1 | DP-R1-11 | F-4.3 | Planned
47 | DP-R4-04 | Salesforce + Pipedrive | R4 | v3.5.1 | DP-R1-07 | F-4.4 | Planned
48 | DP-R4-05 | Executive Intelligence | R4 | v3.5.2 | DP-R2-01,04; DP-R3-02 | F-4.5 | Planned
49 | DP-R4-06 | Ops hardening + residency | R4 | v3.5.2 | DP-R3-RC | F-4.6, F-4.7 | Planned
50 | DP-R4-07 | Customer Intelligence + admin v2 | R4 | v3.5.3 | DP-R3-02 | F-4.8, F-4.9 | Planned
51 | DP-R4-RC | Release cut v3.5 + R5 gate | R4 | v3.5.3 | All R4 | — | Planned
52 | DP-R5-01 | Knowledge Graph foundation | R5 | v4.0 | R4-RC gate | F-5.2 | Planned
53 | DP-R5-02 | Autonomous AI Agents | R5 | v4.0 | DP-R5-01 | F-5.1 | Planned
54 | DP-R5-03 | Multi-modal ingestion | R5 | v4.0.1 | DP-R5-01 | F-5.4 | Planned
55 | DP-R5-04 | Market Intelligence | R5 | v4.0.1 | DP-R5-01 | F-5.5 | Planned
56 | DP-R5-05 | Risk Intelligence | R5 | v4.0.2 | DP-R5-01 | F-5.6 | Planned
57 | DP-R5-06 | SKUs + marketplace + forecasting | R5 | v4.0.3 | Council review | F-5.3, F-5.7, F-5.8 | Planned
58 | DP-R5-RC | Release cut v4.0 + council re-convene | R5 | v4.0.3 | All R5 | — | Planned

## Release Milestones
Release | Version | Window | Theme | Revenue Event | # Features (auto) | Est PD (auto) | Exit Criteria | Status | Actual Ship Date
R0 | v1.1 | Weeks 1-4 | Foundation & Visibility | — (acquisition engine) | 12 | 47 | >50 indexed pages; activation >=20%; organic baseline; API documented | Planned
R1 | v2.0 | Weeks 5-12 | Platform Launch: Social + Connectors + Monetization | Paid tiers go live | 17 | 87 | Free->paid >=3%; WAU/MAU ->40%; 50 paying workspaces; churn <5% | Planned
R2 | v2.5 | Months 4-6 | Competitive & Company Intelligence | Pro-tier expansion | 11 | 66 | WAU/MAU >=40%; D30 retention lift from alerts; Pro mix growing | Planned
R3 | v3.0 | Months 7-9 | Brand, AI Visibility & Content Engine | Add-on revenue begins | 9 | 62 | Free->paid >=5%; add-on attach >=15% | Planned
R4 | v3.5 | Months 10-12 | Enterprise, Trust & Reliability | Enterprise tier opens | 9 | 67 | First 5 enterprise logos; NRR >=110%; SOC 2 issued | Planned
R5 | v4.0 | Year 2 | Autonomous & Predictive Intelligence | Platform licensing | 8 | 101 | Gate: WAU/MAU >=45% & churn <=3% at R4-RC | Planned
|  |  |  | TOTAL | 66 | 430

## Docs & Content
Prompt ID | Feature(s) | Feature Doc | Help Article(s) | Use Case | Changelog Entry | Launch Blog | Runbook | API Ref Update | In-App Copy | Status | Notes
DP-R0-00 | F-000, F-0.9 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R0-01 | F-0.1 | Required | Required | Required | Required | Yes | If worker/queue added | Yes | Required | Planned
DP-R0-02 | F-0.2 | Required | Required | Required | Required | Section in release post | If worker/queue added | Yes | Required | Planned
DP-R0-03 | F-0.3 | Required | Required | Required | Required | Yes | If worker/queue added | Yes | Required | Planned
DP-R0-04 | F-0.4 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R0-05 | F-0.5 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R0-06 | F-0.6 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R0-07 | F-0.7 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R0-08 | F-0.10 | Required | Required | Required | Required | Section in release post | Yes | Yes | Required | Planned
DP-R0-09 | F-0.8 | Required | Required | Required | Required | Yes | If worker/queue added | If endpoints changed | Required | Planned
DP-R0-10 | F-0.11 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R0-RC | Release | N/A | N/A | N/A | Assemble notes | Yes (launch post) | N/A | N/A | What's-new modal | Planned
DP-R1-01 | F-1.1a | Required | Required | Required | Required | Section in release post | Yes | If endpoints changed | Required | Planned
DP-R1-02 | F-1.1b | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R1-03 | F-1.1c | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R1-04 | F-1.1d | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R1-05 | F-1.1e | Required | Required | Required | Required | Yes | Yes | If endpoints changed | Required | Planned
DP-R1-06 | F-1.2 | Required | Required | Required | Required | Yes | Yes | If endpoints changed | Required | Planned
DP-R1-07 | F-1.3, F-1.4, F-1.6 | Required | Required | Required | Required | Yes | Yes | If endpoints changed | Required | Planned
DP-R1-08 | F-1.8, F-1.10 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R1-09 | F-1.5 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R1-10 | F-1.7, F-1.9 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R1-11 | F-1.11 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R1-12 | F-1.12 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R1-13 | F-1.13 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R1-RC | Release | N/A | N/A | N/A | Assemble notes | Yes (launch post) | N/A | N/A | What's-new modal | Planned
DP-R2-01 | F-2.1 | Required | Required | Required | Required | Yes | If worker/queue added | Yes | Required | Planned
DP-R2-02 | F-2.2 | Required | Required | Required | Required | Yes | If worker/queue added | Yes | Required | Planned
DP-R2-03 | F-2.3 | Required | Required | Required | Required | Yes | Yes | If endpoints changed | Required | Planned
DP-R2-04 | F-2.4 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R2-05 | F-2.5 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R2-06 | F-2.6 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R2-07 | F-2.7, F-2.8 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R2-08 | F-2.9, F-2.10, F-2.11 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R2-RC | Release | N/A | N/A | N/A | Assemble notes | Yes (launch post) | N/A | N/A | What's-new modal | Planned
DP-R3-01 | F-3.1 | Required | Required | Required | Required | Yes | If worker/queue added | If endpoints changed | Required | Planned
DP-R3-02 | F-3.2 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R3-03 | F-3.3 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R3-04 | F-3.4 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R3-05 | F-3.5 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R3-06 | F-3.6, F-3.7 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R3-07 | F-3.8, F-3.9 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R3-RC | Release | N/A | N/A | N/A | Assemble notes | Yes (launch post) | N/A | N/A | What's-new modal | Planned
DP-R4-01 | F-4.1 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R4-02 | F-4.2 | Required | Required | Required | Required | Yes | If worker/queue added | If endpoints changed | Required | Planned
DP-R4-03 | F-4.3 | Required | Required | Required | Required | Section in release post | Yes | If endpoints changed | Required | Planned
DP-R4-04 | F-4.4 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R4-05 | F-4.5 | Required | Required | Required | Required | Yes | If worker/queue added | If endpoints changed | Required | Planned
DP-R4-06 | F-4.6, F-4.7 | Required | Required | Required | Required | Section in release post | Yes | If endpoints changed | Required | Planned
DP-R4-07 | F-4.8, F-4.9 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R4-RC | Release | N/A | N/A | N/A | Assemble notes | Yes (launch post) | N/A | N/A | What's-new modal | Planned
DP-R5-01 | F-5.2 | Required | Required | Required | Required | Yes | If worker/queue added | If endpoints changed | Required | Planned
DP-R5-02 | F-5.1 | Required | Required | Required | Required | Yes | If worker/queue added | If endpoints changed | Required | Planned
DP-R5-03 | F-5.4 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R5-04 | F-5.5 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R5-05 | F-5.6 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R5-06 | F-5.3, F-5.7, F-5.8 | Required | Required | Required | Required | Section in release post | If worker/queue added | If endpoints changed | Required | Planned
DP-R5-RC | Release | N/A | N/A | N/A | Assemble notes | Yes (launch post) | N/A | N/A | What's-new modal | Planned

## RAID Log
ID | Type | Description | Release/Prompt | Severity | Likelihood | Mitigation / Action | Owner | Status | Date Raised | Date Closed
R-01 | Risk | X/Twitter API pricing or limit changes break Social economics | R1 / DP-R1-01 | High | Medium | Reddit+RSS-first value; X Pro-gated; collector-level quotas; monitor monthly | Ops | Open | 2026-08-06
R-02 | Risk | HubSpot App Marketplace approval delays connector GA | R1 / DP-R1-07 | Medium | Medium | Applied Week 0; private-app fallback for beta | BE Lead | Open | 2026-08-06
R-03 | Risk | Classifier accuracy below gate (esp. hi/en code-mix) | R1 / DP-R1-02 | High | Medium | Golden-set gate 80/70; hosted-LLM fallback pre-approved; feedback loop grows eval set | ML | Open | 2026-08-06
R-04 | Risk | Programmatic SEO pages flagged as thin content | R0 / DP-R0-05 | Medium | Medium | Quality gate; unique cached data per page; 100-page pilot + GSC watch | Growth | Open | 2026-08-06
R-05 | Risk | CRM write errors damage customer trust | R1 / DP-R1-07 | High | Low | Dry-run default on first sync; per-field toggles; undo window; sync log | BE Lead | Open | 2026-08-06
R-06 | Risk | AEO provider ToS or API variability | R3 / DP-R3-01 | Medium | Medium | Official APIs only; per-provider ADR; graceful degradation; public methodology | PM | Open | 2026-08-06
R-07 | Risk | LinkedIn/Meta source access not granted | R3 / DP-R3-06 | Medium | High | 5-day spike gate; parallel partnership applications; roadmap honesty on marketing pages | PM | Open | 2026-08-06
R-08 | Risk | Alert fatigue drives notification opt-out | R1 / DP-R1-05 | Medium | Medium | 30-min suppression; sane defaults; weekly digest default | PM | Open | 2026-08-06
A-01 | Assumption | Stack is Next.js + Supabase + Redis (per council ADR requirement, verify in DP-R0-00) | R0 | High | — | ADR-001 records actual stack; prompts adapt | Eng | Open | 2026-08-06
A-02 | Assumption | Team of 3-5 engineers + designer available (or AI-agent equivalent capacity) | All | High | — | Confirm with founder; prompt granularity supports solo+agents mode | Founder | Open | 2026-08-06
A-03 | Assumption | X API Basic budget ($100/mo) approved | R1 | Medium | — | Founder sign-off before DP-R1-01 | Founder | Open | 2026-08-06
D-01 | Dependency | Stripe account + tax registration (India GST review) | R1 / DP-R1-06 | High | — | Ops task flagged to founder; Stripe Tax enablement | Founder | Open | 2026-08-06
D-02 | Dependency | Salesforce AppExchange security review lead time | R4 / DP-R4-04 | Medium | — | File during R3 | BE Lead | Open | 2026-08-06
D-03 | Dependency | SOC 2 auditor engagement | R4 / DP-R4-02 | High | — | Evidence collection from R2; auditor selection at R3-RC | Ops | Open | 2026-08-06
I-01 | Issue | Live site SPA still serves only head metadata to crawlers (confirmed Aug 2026) | R0 / DP-R0-01 | High | — | Resolved by permalinks + SSR work in R0 | Eng | Open | 2026-08-06