## Scoring Model
DatIQ — Prioritised Features Release Roadmap · Backlog Tracker
Produced by a 4-member AI Model Council (Growth/Conversion · Market Strategy · Retention/UX · Platform Engineering) synthesising 6 model reports (Gemini, Perplexity, ChatGPT, Grok, DeepSeek, Meta AI) + live datiq.app review. July 16, 2026.
Scoring weights (edit the blue cells — Value and Priority recalculate)
CONV — Conversion-rate impact | 22%
REACH — Market reach / acquisition | 16%
ENG — Engagement & retention | 20%
EQ — Efficiency & output quality | 12%
DIFF — Differentiation | 15%
MON — Monetisation fit | 15%
Weights total | 100%
Formulas
Value (0–5) = Σ(score × weight) across the six parameters
Priority Index = Value × (1 + 0.05 × Council Votes) ÷ √Effort — √Effort keeps large strategic bets comparable to quick wins
Council Votes = number of the 4 council members who placed the feature in their top-12 (or proposed it)
All parameter scores (0–5) are averages of council-member scores where available, else chair-assigned from the source reports. Effort is in person-months (dev+design+QA).
Note: Rankings guide sequencing but release assignment also honours hard dependencies (see Release Plan sheet).

## Prioritised Backlog
ID | Feature | Category | Release | CONV | REACH | ENG | EQ | DIFF | MON | Effort (pm) | Council Votes | Value (0–5) | Priority Index | Overall Rank | Sources | Council Notes
F01 | One-click Export (CSV / JSON / Clipboard / Google Sheets) | Quick Win | R1 · v2.1 | 5 | 2 | 3.3 | 5 | 0 | 3.3 | 0.4 | 3 | 3.18 | 5.78 | 1 | Perplexity, ChatGPT, Grok, DeepSeek, Gemini | Table stakes across every competitor; #1 trial-killer today — value dies on-screen. Unanimous council support.
F02 | Accounts + Saved Extraction History | Quick Win | R1 · v2.1 | 4.3 | 2 | 5 | 3.3 | 0.7 | 4 | 1.3 | 3 | 3.37 | 3.4 | 10 | All 5 on-topic reports; Council A/C/D | Substrate for every later feature (collections, monitoring, API keys, teams). Free tier capped at 10 items = upgrade trigger.
F07 | "Extract Similar" Post-result CTA | Quick Win | R1 · v2.1 | 3.5 | 1 | 4.5 | 3 | 2 | 3.5 | 0.4 | 2 | 3.02 | 5.25 | 2 | DeepSeek (9.5/10 top pick); Council A/C | Cheapest session-depth multiplier; turns 1 extraction into 4, burns trial quota faster, hits paywall sooner.
F09 | AI Output Feedback Widget (thumbs up/down + comment) | Quick Win | R1 · v2.1 | 2 | 0 | 3 | 5 | 1 | 1 | 0.5 | 1 | 1.94 | 2.88 | 16 | Perplexity; Council C | Instruments perceived output quality — the silent retention variable; feeds extraction-quality improvement loop.
F10 | Keyboard Shortcuts / Power-user Mode | Quick Win | R1 · v2.1 | 1 | 0 | 2 | 2 | 1 | 1 | 0.5 | 0 | 1.16 | 1.64 | 47 | Perplexity | Low-cost delight for analysts and power users.
F13 | Transparent Pricing Page + Tier-Feature Mapping | Quick Win | R1 · v2.1 | 4 | 2.5 | 0 | 0 | 0.5 | 4.5 | 0.25 | 2 | 2.03 | 4.47 | 3 | ChatGPT, DeepSeek; Council A/B | Buyers comparison-shop ruthlessly; an uncrawlable pricing page loses deals before they start.
F14 | Privacy & Trust Messaging + Data-retention Statement | Quick Win | R1 · v2.1 | 2 | 1 | 1 | 2 | 1 | 3 | 0.25 | 1 | 1.64 | 3.44 | 8 | Meta AI (transferable), Council D | 'Data deleted after Xd, no training on your data' under the input box; table stakes before Agency/API deals.
F15 | Onboarding Tooltips / First-run Product Tour | Quick Win | R1 · v2.1 | 3 | 0 | 2 | 2 | 0 | 1 | 0.5 | 0 | 1.45 | 2.05 | 38 | Copilot (transferable), Perplexity | Clarifies the 8 extraction modes on first visit; pairs with F06 recipe chips.
F50 | Product Analytics + A/B Instrumentation (foundational) | Platform Foundation | R1 · v2.1 | 1.5 | 0.5 | 2.5 | 3.5 | 0 | 1.5 | 0.9 | 2 | 1.56 | 1.81 | 44 | Copilot (transferable), Council C/D | Non-negotiable: every later prioritisation claim is untestable without funnel + retention telemetry.
FA3 | In-product Paywall / Quota-exhaustion Upgrade Flow + Annual Plans | Quick Win | R1 · v2.1 | 5 | 0 | 0 | 0 | 0 | 5 | 0.5 | 1 | 1.85 | 2.75 | 18 | Council A (new) | Upgrade screen at the exact moment of trial exhaustion, showing which paid feature completes the current task; annual anchoring.
F04 | Shareable Result Permalinks + SSR ("Powered by DatIQ" loop) | Growth & PLG | R2 · v2.2 | 4.5 | 5 | 3.5 | 2 | 3.5 | 2 | 1.5 | 2 | 3.56 | 3.2 | 13 | ChatGPT (#1, 4.15), Perplexity, Meta AI; Council A/B | Every extraction becomes an indexed, shareable landing page — fixes SEO invisibility + creates the viral loop. Requires FD2 cache; ship after accounts (Council C condition) with DMCA takedown process (Council D condition).
F05 | Homepage Animated Demo + Example Gallery + Prompt Chips | Growth & PLG | R2 · v2.2 | 4 | 3 | 1 | 1 | 1 | 1 | 0.75 | 1 | 1.98 | 2.4 | 30 | Perplexity (#1, 43.2), Meta AI, DeepSeek | Pre-filled animated extraction on a known URL = instant aha with zero signup friction; prompt chips teach what to ask.
F06 | Persona Onboarding + Recipe Packs (Sales Pack, CI Pack, SEO Pack…) | Growth & PLG | R2 · v2.2 | 5 | 2 | 3.5 | 4 | 2 | 3 | 1.25 | 2 | 3.35 | 3.3 | 11 | Perplexity, DeepSeek (9.0), Browse AI benchmark; Council A/C | Routes SDRs to Contacts and analysts to Pricing in <60s; blank-box tools bleed activation.
F11 | Programmatic SEO + Persona Landing Routes (/for-sales, /extract-pricing…) | Growth & PLG | R2 · v2.2 | 3 | 5 | 1 | 1 | 2 | 2 | 1 | 2 | 2.38 | 2.62 | 22 | ChatGPT (4.00), Perplexity; Council A/B | Near-zero SEO footprint in a 13-19% CAGR category; long-tail intent pages the single home URL can never capture.
F12 | Public Changelog + Product Hunt / Social Launch | Growth & PLG | R2 · v2.2 | 2 | 4 | 1 | 0 | 0 | 1 | 0.5 | 1 | 1.43 | 2.12 | 35 | ChatGPT (3.75); Council A | v2 needs a launch moment; changelog builds trust and re-engagement.
FA1 | Free-tier "Public Report" Quota Mechanic | Growth & PLG | R2 · v2.2 | 4 | 5 | 3 | 1 | 4 | 3 | 0.75 | 1 | 3.45 | 4.18 | 5 | Council A (new) | Unlimited free extractions if published as public indexed DatIQ-branded pages; private runs consume quota. Feeds F04/F11 content flywheel.
FA2 | Referral Credits Loop (give 25 / get 25) | Growth & PLG | R2 · v2.2 | 3 | 4 | 2 | 0 | 1 | 3 | 0.5 | 1 | 2.3 | 3.42 | 9 | Council A (new) | Triggered at quota-exhaustion moment; classic PLG, near-zero build.
FB1 | Competitor Comparison Pages + Battle-card Generator (/vs/firecrawl…) | Growth & PLG | R2 · v2.2 | 4 | 5 | 2 | 2 | 3 | 2 | 1 | 1 | 3.07 | 3.22 | 12 | Council B (new) | Comparison keywords = highest-intent SaaS traffic; 'compare 2 competitor URLs → diff table' demos the product while ranking for it.
F03 | Collections / Projects Workspace | Retention & Workflow | R3 · v3.0 | 2 | 1 | 5 | 3 | 2 | 4 | 2.5 | 1 | 2.86 | 1.9 | 41 | Perplexity, Grok, DeepSeek (Intelligence Hub); Council C | Named research projects (e.g. 'Q3 Competitor Research'); organised accumulation = switching cost; data model for teams later.
F16 | Batch Enhancements (CSV URL upload, results table, parallel runs) | Retention & Workflow | R3 · v3.0 | 3.5 | 1.5 | 3.5 | 5 | 1 | 4 | 1.75 | 2 | 3.06 | 2.54 | 25 | All reports; batch exists in trial — deepen it | Forces the queue/worker/retry architecture needed for monitoring + API anyway; closes gap vs Hunter bulk & Clay.
F17 | Scheduled Monitoring + Change Detection Alerts (email/Slack) | Retention & Workflow | R3 · v3.0 (beta) → R4 GA | 3.5 | 2.5 | 5 | 3.5 | 3 | 5 | 2.4 | 4 | 3.79 | 2.94 | 15 | ALL 5 reports + all 4 council members (only unanimous feature) | Converts one-shot tool into recurring-value subscription; the D30 retention engine and strongest $29/mo justification. Schedule tab exists — add diffing + alerting. GA gated on F36.
F18 | Google Sheets / Airtable / Notion Export Integrations | Retention & Workflow | R3 · v3.0 | 3 | 3 | 3 | 3 | 1 | 4 | 1.5 | 0 | 2.85 | 2.33 | 31 | ChatGPT, Grok, DeepSeek | Where extracted data actually lives for non-technical personas; cheapest 'integrations' checkbox.
F36 | Anti-bot / Proxy / JS-rendering Infrastructure | Platform Foundation | R3 · v3.0 | 3 | 2 | 4 | 5 | 2 | 3 | 2.5 | 1 | 3.13 | 2.08 | 36 | Gemini, DeepSeek, Bright Data benchmark; Council D (#1) | ~40% of target pages are JS-heavy or bot-protected; existential dependency for batch-at-scale, monitoring GA and API credibility.
F49 | Deep-linked Re-engagement Emails ('your schedule ran / data changed') | Retention & Workflow | R3 · v3.0 | 2 | 1 | 4 | 2 | 0 | 2 | 1 | 1 | 1.94 | 2.04 | 40 | Copilot (transferable); Council C | Free D7 lift once accounts + monitoring exist; deep links resume exact context.
FC1 | Watchlist Home (logged-in dashboard: monitored URLs, deltas, re-run) | Retention & Workflow | R3 · v3.0 | 3 | 1 | 5 | 3 | 3 | 3 | 1.5 | 1 | 3.08 | 2.64 | 21 | Council C (new); Grok (dashboard/history feed) | The 'Bloomberg-terminal opening screen' for web data; gives history + monitoring a daily-open surface.
FD2 | Idempotent Job Queue + Result Cache + Dedup | Platform Foundation | R3 · v3.0 | 1 | 0 | 2 | 5 | 1 | 3 | 1.5 | 1 | 1.82 | 1.56 | 48 | Council D (new) | Same URL twice in an hour = one fetch; cuts infra cost 30-50%, makes permalinks instant and monitoring predictable.
FD3 | robots.txt / ToS Compliance Engine + Per-domain Rate Limiting | Platform Foundation | R3 · v3.0 | 1 | 1 | 1 | 4 | 2 | 4 | 1 | 1 | 1.96 | 2.06 | 37 | Council D (new) | Prevents shared-infra IP bans (one abusive user blackholes everyone); the compliance story enterprise buyers ask about first.
F08 | Preset Schema Auto-detection from URL Patterns | Integrations & Ecosystem | R4 · v3.5 | 3 | 1 | 3 | 4 | 3 | 2 | 1 | 0 | 2.65 | 2.65 | 20 | Gemini (top pick, 16.0) | Regex + semantic URL analysis auto-suggests product/job/article schema; reduces configuration friction.
F19 | Zapier / Make / Webhooks | Integrations & Ecosystem | R4 · v3.5 | 3 | 3.5 | 3 | 2.5 | 1 | 3.5 | 1 | 2 | 2.8 | 3.08 | 14 | Perplexity, ChatGPT, Grok, DeepSeek; Council A/B | Zapier directory listing is itself an acquisition channel; 'URL extracted → push to Sheet/Notion/HubSpot' = live data pipeline.
F21 | Public REST API + Key Management + Usage Metering | Integrations & Ecosystem | R4 · v3.5 | 3 | 4 | 3.5 | 3.5 | 2 | 5 | 2.2 | 2 | 3.47 | 2.57 | 23 | Perplexity, ChatGPT, DeepSeek, Gemini; Council B/D | Unlocks dev/AI segment + usage-based revenue; B2B2B distribution. Needs F02 + rate limiting.
F22 | SDK Code-snippet Exporter (Python / Node / cURL from any manual run) | Integrations & Ecosystem | R4 · v3.5 | 3 | 3 | 2 | 4 | 2 | 4 | 0.5 | 1 | 2.92 | 4.34 | 4 | Gemini (top-3, 16.0); Council D | Pure templating over the API; converts UI users into API users.
F23 | MCP Server (DatIQ as native tool for Claude/GPT/Cursor agents) | Integrations & Ecosystem | R4 · v3.5 | 2.5 | 5 | 3 | 3 | 4 | 4 | 1.25 | 2 | 3.51 | 3.45 | 7 | Gemini (15.63), Perplexity, ChatGPT; Council B/D | Thin wrapper over the API; the agent ecosystem is 2026's fastest-growing distribution channel. Ship persona-flavoured tools (extract_pricing, find_contacts).
F24 | LLM-ready Markdown Export (RAG/agent pipelines) | Integrations & Ecosystem | R4 · v3.5 | 2 | 4 | 2 | 4 | 2 | 3 | 0.5 | 1 | 2.71 | 4.02 | 6 | Perplexity, ChatGPT, Firecrawl benchmark; Council D | Near-free (DOM already parsed); rides the RAG wave; captures the AI-engineer persona.
F25 | Prebuilt Schema / Template Library (e-com, jobs, news, SaaS pricing…) | Integrations & Ecosystem | R4 · v3.5 | 4 | 5 | 3 | 4 | 3 | 3 | 2 | 1 | 3.66 | 2.72 | 19 | All reports; Browse AI (150+) benchmark; Council B | Each template doubles as an indexed SEO landing page (Browse AI's engine); typed JSON output serves developers too.
F42 | Teams Pricing Tier + Usage-based Add-ons + Paid API Tier | Integrations & Ecosystem | R4 · v3.5 | 2 | 2 | 2 | 1 | 1 | 5 | 1.5 | 1 | 2.18 | 1.87 | 42 | DeepSeek (monetisation section); Council A/B | Teams $79-99/mo, metered API, enterprise custom; replaces 'Agency unlimited' abuse magnet. Sell seats before building full RBAC.
FC3 | Weekly "Your Data Changed" Digest (auto-diff summary email) | Retention & Workflow | R4 · v3.5 | 2 | 2 | 4 | 3 | 2 | 3 | 1 | 1 | 2.67 | 2.8 | 17 | Council C (new); Perplexity digest idea | Persona-valuable habit loop (not gamification fluff); extends monitoring value between sessions.
F20 | Chrome Extension (one-click extract on current tab) | Intelligence & Quality | R5 · v4.0 | 3.3 | 4.7 | 4.3 | 3 | 2.7 | 3 | 2.7 | 3 | 3.55 | 2.48 | 27 | All 5 reports (Grok #1, DeepSeek 9.0); Council A/B/C | Chrome Web Store = free discovery surface; ambient retention; Thunderbit/Hunter prove the wedge.
F26 | Tech Stack Detection (BuiltWith/Wappalyzer-style) | Intelligence & Quality | R5 · v4.0 | 3 | 3 | 3 | 3 | 4 | 3 | 1.5 | 0 | 3.15 | 2.57 | 23 | Perplexity (7.7) | High-value intel for SDRs (what CRM do they use?), VCs and devs; unique vs current no-code competitors.
F27 | Domain Intelligence Dashboard (live company one-pager) | Intelligence & Quality | R5 · v4.0 | 4 | 4 | 4 | 4 | 5 | 4 | 3 | 1 | 4.15 | 2.52 | 26 | Perplexity, Grok; Council B (category-creating framing) | All URLs + structure + contacts + tech + latest content for any domain — a mini-Diffbot at 1/50th the price; serves VC, SDR and CI at once.
F28 | Email Verification / Deliverability Scoring | Intelligence & Quality | R5 · v4.0 | 3 | 2 | 2 | 5 | 3 | 5 | 3 | 0 | 3.18 | 1.84 | 43 | Perplexity, ChatGPT, Hunter benchmark | A verified email is worth 5-10x a raw scraped address; credit-based monetisation aligned with Hunter's model.
F35 | Self-healing Extraction + Validation Layer | Intelligence & Quality | R5 · v4.0 | 3 | 1 | 4 | 5 | 5 | 4 | 3 | 1 | 3.57 | 2.16 | 33 | ChatGPT, Gemini, Kadoa benchmark; Council D | Semantic re-location of fields when layouts change; drift detection; silent-wrong-data kills trust faster than errors.
F48 | User Analytics Dashboard (usage, quota, insights unlocked) | Retention & Workflow | R5 · v4.0 | 2 | 0 | 3 | 2 | 1 | 2 | 1 | 0 | 1.73 | 1.73 | 46 | Grok, Copilot (transferable) | Transparency into consumption; natural upgrade prompt surface.
FB2 | Free Public Micro-tools (email finder, pricing extractor, sitemap visualiser) | Growth & PLG | R5 · v4.0 | 3 | 5 | 1 | 2 | 2 | 2 | 1.5 | 1 | 2.5 | 2.14 | 34 | Council B (new); Hunter's playbook | Each micro-tool = a distinct indexed page funnelling to signup; Hunter built its entire top-of-funnel this way.
FC2 | Per-field Confidence Badges + Inline "Fix this field" Corrections | Intelligence & Quality | R5 · v4.0 | 3 | 0 | 3 | 5 | 4 | 2 | 2 | 1 | 2.76 | 2.05 | 38 | Council C (new) | One-click correction retrains the schema; builds trust and a proprietary quality dataset.
FD1 | Extraction Reliability Layer (status page, confidence scores, retry ladder) | Intelligence & Quality | R5 · v4.0 | 3 | 1 | 4 | 5 | 4 | 3 | 2 | 1 | 3.27 | 2.43 | 28 | Council D (new) | fetch → headless → proxy fallback + per-result confidence; the 'it just works' difference between toy and tool.
F30 | CRM Integrations (HubSpot first, then Salesforce/Pipedrive) | Teams & Enterprise | R6 · v4.5 | 3 | 3 | 3 | 3 | 3 | 5 | 2.5 | 1 | 3.3 | 2.19 | 32 | Perplexity, DeepSeek; Council B | 'URL → enriched HubSpot record' is a Clay-lite pitch at a tenth the price; SDR willingness-to-pay lives here.
F31 | Team Workspaces + RBAC + Shared History | Teams & Enterprise | R6 · v4.5 | 2 | 2 | 3 | 2 | 1 | 5 | 3 | 0 | 2.5 | 1.44 | 52 | All reports; Council consensus: AFTER F02→F03 and Teams-tier demand proof | Primary unlock for team/enterprise pricing; deliberately sequenced after collections prove multiplayer demand.
F32 | Competitor Change-Intelligence Feed (curated CI dashboard) | Teams & Enterprise | R6 · v4.5 | 2 | 2 | 4 | 3 | 4 | 4 | 4 | 0 | 3.12 | 1.56 | 48 | Perplexity (4.5); Browse AI mid-market benchmark | Vertical SaaS product for PM/strategy teams: pricing updates, feature launches, team changes in one feed; builds on monitoring.
F41 | SOC 2 / GDPR Compliance Program | Teams & Enterprise | R6 · v4.5 | 1 | 1 | 0 | 2 | 1 | 4 | 3 | 0 | 1.37 | 0.79 | 62 | ChatGPT; Council D | Trigger-based: pursue when enterprise deals or design-partner pipeline justify the spend.
F44 | Localization / Multilingual Extraction + India-first GTM | Teams & Enterprise | R6 · v4.5 | 2 | 4 | 2 | 2 | 3 | 2 | 2.5 | 0 | 2.47 | 1.56 | 48 | Meta AI (transferable: Hinglish, regional pricing) | Nobody in the category does India-first; large underserved SMB/analyst market; pairs with regional payment methods.
F29 | Waterfall Enrichment (multi-source sequential fill) | Agentic Vision | R7 · v5.0+ | 2 | 2 | 3 | 4 | 4 | 4 | 5 | 0 | 3.04 | 1.36 | 55 | Perplexity, DeepSeek; Clay's signature innovation | Start with 2-source fallback (own extraction + email lookup); full waterfall is a Clay-scale project.
F33 | Interactive Action Sandbox (logins, clicks, auth/paywalled pages) | Agentic Vision | R7 · v5.0+ (legal-gated) | 2 | 2 | 3 | 4 | 4 | 3 | 5 | 0 | 2.89 | 1.29 | 57 | Gemini, Firecrawl/Browserbase benchmark; Council D: KILL until legal cleared | CFAA/ToS/GDPR minefield + credential-vault burden; revisit only post-F41 with counsel.
F34 | "DatIQ Agent" — Autonomous Multi-step NL Research Crawler | Agentic Vision | R7 · v5.0+ | 3 | 3 | 4 | 3 | 5 | 4 | 6 | 0 | 3.65 | 1.49 | 51 | Gemini, Perplexity (Claygent parity); Council verdict: unanimous DELAY 12 months | 'Find CEO, pricing, tech stack for these 30 companies' autonomously. Gated on F35+F36 reliability and unit economics (20-50x per-run cost).
F37 | Full-page Snapshots / Archiving (anti-link-rot) | Agentic Vision | R7 · v5.0+ | 1 | 1 | 3 | 3 | 2 | 2 | 2 | 0 | 1.94 | 1.37 | 54 | Grok | Historical archive of monitored pages; useful for CI/legal use cases.
F38 | AI Chat over Saved Library (ask questions across all saved extractions) | Agentic Vision | R7 · v5.0+ | 2 | 2 | 5 | 4 | 4 | 4 | 4 | 1 | 3.44 | 1.81 | 44 | Grok (signature idea); Council C | Makes the accumulated library compounding, not just stored; RAG over user's own research corpus.
F39 | Knowledge Graph / Entity Enrichment | Agentic Vision | R7 · v5.0+ | 1 | 2 | 2 | 3 | 4 | 3 | 6 | 0 | 2.35 | 0.96 | 60 | ChatGPT, Perplexity; Diffbot benchmark | Entity resolution across extractions; long-term differentiator, premature before scale.
F40 | Template Marketplace (creator monetisation) | Agentic Vision | R7 · v5.0+ | 1 | 2 | 2 | 1 | 3 | 3 | 4 | 0 | 1.96 | 0.98 | 59 | DeepSeek, Meta AI (transferable); Council B: revisit at 10k users | Marketplace economics need thousands of MAU creators; ship first 100 templates in-house (F25) instead.
F43 | Public Gallery / Remix of Shared Reports | Agentic Vision | R7 · v5.0+ | 1 | 3 | 2 | 1 | 2 | 1 | 2 | 0 | 1.67 | 1.18 | 58 | Meta AI (transferable) | Network-effect play once shared permalinks (F04) reach volume.
F45 | Mobile / PWA Optimisation | Agentic Vision | R7 · v5.0+ | 1 | 2 | 2 | 1 | 0 | 1 | 2 | 0 | 1.21 | 0.86 | 61 | DeepSeek (6.5, lowest), Copilot (transferable) | Desk-work product; lowest council enthusiasm; PWA basics only.
F46 | Milestones / Gamification ('50 companies analysed!') | Agentic Vision | R7 · v5.0+ | 1 | 1 | 3 | 1 | 1 | 1 | 1 | 0 | 1.4 | 1.4 | 53 | Perplexity, Copilot (transferable); Council B: 'retention theatre' | Folded into FC3 digest; badges on a tool with no habit loop is decoration.
F47 | Split-screen Live Render Preview | Agentic Vision | R7 · v5.0+ | 2 | 0 | 2 | 3 | 2 | 1 | 1.5 | 0 | 1.65 | 1.35 | 56 | Gemini | Visual confirmation of extraction accuracy; nice-to-have after confidence badges (FC2).
FB3 | Lookalike Company Discovery ('find 25 similar companies') | Agentic Vision | R7 · v5.0+ | 4 | 3 | 4 | 4 | 4 | 5 | 3 | 1 | 3.99 | 2.42 | 29 | Council B (new); Clay/Ocean.io benchmark | Turns one extraction into a prospecting list; massively raises SDR willingness-to-pay.

## Release Plan
Release | Theme | Timeframe | Objective | # Features | Total Effort (pm) | Success Criteria / KPIs
R1 · v2.1 | Convert & Keep | 0–6 weeks (Aug 2026) | Stop the leaks: make value portable, persistent and purchasable. Fix activation→conversion before buying traffic. | 10 | 5.5 | D1 activation ≥40% (2+ extractions + 1 export); free→paid ≥3%; baseline telemetry live
R2 · v2.2 | Launch & Be Found | 6–12 weeks (Sep–Oct 2026) | Acquisition flywheel: every result a shareable indexed page; persona routes; public launch moment. | 8 | 7.3 | Indexed pages >50; organic visits baseline; referral K-factor >0.15; PH launch top-5 of day
R3 · v3.0 | Habit & Reliability | Q4 2026 | Turn one-shot use into weekly habit; harden the engine (JS rendering, queue, compliance) that everything else depends on. | 9 | 15.7 | D7 retention 2× baseline; extractions/session ≥3; monitoring beta on 500 URLs; fetch success ≥95%
R4 · v3.5 | Ecosystem & Developers | Q1 2027 | Open the platform: API, SDK, MCP, Zapier, template library; monetisation architecture (Teams tier, metered API). | 9 | 11 | API signups; MCP installs; Zapier listing live; WAU/MAU ≥40%; free→paid ≥5%
R5 · v4.0 | Intelligence & Quality | Q2–Q3 2027 | Differentiate on being right: self-healing, confidence scoring, verified emails, tech-stack + domain intelligence; extension distribution. | 9 | 19.7 | Extraction accuracy ≥97% on template set; verified-email credits revenue; extension WAU; D30 retention 2×
R6 · v4.5 | Teams & Enterprise | Q4 2027 | Multiplayer + enterprise readiness: workspaces, CRM, SOC2 (trigger-based), CI feed as vertical product. | 5 | 15 | Multi-seat accounts ≥15% of revenue; first enterprise deals; NRR >110%
R7 · v5.0+ | Agentic Vision | 2028+ | Category creation: autonomous research agent, chat-over-library, lookalikes, waterfall enrichment, knowledge graph. | 12 | 41.5 | Agent unit economics positive; library-chat WAU; ARPU expansion
Effort sums use the Effort column of the Prioritised Backlog; features spanning releases (e.g. F17 beta→GA) are counted in their first release.

## Council Verdicts
Debate | Positions | Council Resolution
Ship viral permalinks (F04) first vs. fix retention first | Growth (A) + Market (B) wanted F04 in first release; Retention (C) objected — sharing into a stateless product amplifies churn; Engineering (D) flagged DMCA + cache dependency. | RESOLVED: F04 ships in R2, immediately after accounts/history (R1) and with the FD2 result-cache and a takedown process. Viral loop lands on a product that can retain the users it acquires.
Monitoring now vs. infrastructure first | All four members back monitoring (F17) — the only unanimous feature. Engineering (D) insisted a monitor that silently breaks on redesigns is a churn event with a paying customer attached. | RESOLVED: F17 beta in R3 on a curated domain set, GA in R4 gated on anti-bot/JS infra (F36) and retry ladder (FD1 partial). C accepted the sequencing.
Developer lane (API/MCP) vs. non-developer focus | Growth (A) challenged the dev play — Firecrawl owns that lane at $16/mo. Market (B) countered that MCP is distribution, not a head-on dev fight; Engineering (D) showed F23 is a thin wrapper once F21 exists. | RESOLVED: API+MCP in R4 as a distribution channel with persona-flavoured tools (extract_pricing, find_contacts) rather than a raw-scraping API price war. Primary positioning stays no-code.
Autonomous agent as flagship vs. science project | Gemini + Perplexity reports pitched agentic crawling as the future; every council member voted DELAY/KILL for 12 months — cost 20-50x per run, compounding error rates, no reliability layer yet. | RESOLVED: F34 parked in R7 (2028+), explicitly gated on F35 self-healing, F36 infra, and positive unit economics. MCP (F23) carries the 'agent-ready' narrative meanwhile.
Team features now vs. teams pricing first | DeepSeek + Grok pushed team workspaces early; Growth (A): with 11 teams total there is no multiplayer demand yet — 'sell seats, then build for them.' | RESOLVED: Teams *pricing tier* (F42) in R4; full workspaces/RBAC (F31) in R6 after collections (F03) prove shared-work demand. Dependency chain F02→F03→F31 respected.
Auth/paywalled-page extraction (F33) | Gemini ranked the action sandbox high (10.0); Engineering (D) flagged CFAA/ToS/GDPR exposure and credential-vault security burden a small team cannot carry. | RESOLVED: KILLED from the 18-month roadmap; revisit post-SOC2 (F41) with legal counsel only.
Wrong-product source reports | Copilot analysed a dating app; Meta AI analysed a spreadsheet-analysis product (datiq.netlify.app). Council screened both for transferable ideas rather than discarding. | RESOLVED: Salvaged — onboarding tooltips (F15), re-engagement deep links (F49), analytics discipline (F50) from Copilot; prompt chips (F05), privacy reassurance (F14), localization (F44), micro-tool/gallery patterns from Meta AI. All product-specific recommendations (swipe mechanics, spreadsheet connectors) excluded.